## Sprint 1
Sprint Backlog | [9 empty] | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19
Sprint | Epic ID | Epic name | User Story ID | User Story | Task | Volunteer |  | Status | Estimate Man-Hour | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Sprint Review
Sprint1 | EPIC 1 | Co-working Space Life Cycle Management | US1-1 | As a co-working space owner I want to send a request to add a new co-working space So that I can add my co-working space to the platform, enabling visibility to users | Redesign Schemas (Users, Co-working spaces) | Sutarasil (Jong) | Nathakorn (Oat) | Done | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Design co-working space management page | Sutarasil (Jong) | Papangkon (Nin) | Todo | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement new co-working space request API | Papangkon (Nin) | Theerith (Jianfong) | Done | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
[5 empty] | Implement new co-working space request frontend | Pongpanot (Munich) | Theerith (Jianfong) | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
[5 empty] | QA-Testing | Tanakit (Prom) | Papangkon (Nin) | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
|  |  | US1-2 | As an admin I want to approve a new co-working space requested by the owner So that I can validate the existence and quality of co-working spaces | Design admin approval dashboard listing | Pongpanot (Munich) | Siravit (Bill) | Todo | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement backend logic for approval/rejection. | Theerith (Jianfong) | Siravit (Bill) | Done | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[5 empty] | Implement notification system for owner on approval/rejection. | Theerith (Jianfong) | Siravit (Bill) | Done | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[5 empty] | Implement approval dashboard frontend | Pongpanot (Munich) | Siravit (Bill) | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
[5 empty] | QA-Testing | Patarakrit (Zen) | Tanakit (Prom) | Todo | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  | US1-3 | As a co-working space owner I want to update my co-working space details So that the co-working space details on the platform are up to date | Implement update API for co-working space details | Tanakit (Prom) | Siravit (Bill) | Done | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
[5 empty] | Implement update co-working space form frontend | Theerith (Jianfong) | Pongpanot (Munich) | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
[5 empty] | QA-Testing | Papangkon (Nin) | Patarakrit (Zen) | Todo | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  | US1-4 | As a co-working space owner I want to add new rooms to the co-working space on the platform So that the co-working space details on the platform are up to date | Redesign Schemas (Co-working space, Room) | Nathakorn (Oat) | Tanakit (Prom) | Done | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Design co-working space [id] management page | Khanaphat (Putter) | Patarakrit (Zen) | Todo | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement room creation API | Sutarasil (Jong) | Nathakorn (Oat) | Done | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
[5 empty] | Implement room creation form frontend | Sutarasil (Jong) | Nathakorn (Oat) | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
[5 empty] | QA-Testing | Papangkon (Nin) | Nathakorn (Oat) | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  | US1-5 | As a co-working space owner I want to update rooms in the co-working space on the platform So that the co-working space details on the platform are up to date | Implement room update API. | Patarakrit (Zen) | Siravit (Bill) | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
[5 empty] | Implement room update form frontend | Patarakrit (Zen) | Theerith (Jianfong) | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[5 empty] | QA-Testing | Papangkon (Nin) | Patarakrit (Zen) | Todo | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  | US1-6 | As a co-working space owner I want to delete rooms from the co-working space on the platform So that the co-working space details on the platform are up to date | Design room deletion confirmation UI flow | Pongpanot (Munich) | Siravit (Bill) | Todo | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement room deletion and reservation cleanup logic | Papangkon (Nin) | Khanaphat (Putter) | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
[5 empty] | Implement room cascade deletion for associated bookings | Tanakit (Prom) | Khanaphat (Putter) | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
[5 empty] | Implement room deletion form frontend | Tanakit (Prom) | Khanaphat (Putter) | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[5 empty] | QA-Testing | Patarakrit (Zen) | Tanakit (Prom) | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
|  |  | US1-7 | As a co-working space owner I want to temporarily disable my co-working space on the platform So that I can go on vacation | Implement logic to hide space from search results | Sutarasil (Jong) | Nathakorn (Oat) | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[5 empty] | Implement notification to users with active bookings on disable | Sutarasil (Jong) | Nathakorn (Oat) | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
[5 empty] | Implement room disable frontend | Sutarasil (Jong) | Nathakorn (Oat) | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[5 empty] | QA-Testing | Sutarasil (Jong) | Nathakorn (Oat) | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  | US1-8 | As a co-working space owner I want to re-enable my co-working space on the platform So that customers can view and book my co-working space again after the vacation | Implement logic to restore visibility in system search | Tanakit (Prom) | Khanaphat (Putter) | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[5 empty] | Implement notification to users that the co-working space is available again | Tanakit (Prom) | Khanaphat (Putter) | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
[5 empty] | Implement room re-enable frontend | Theerith (Jianfong) | Siravit (Bill) | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[5 empty] | QA-Testing | Papangkon (Nin) | Patarakrit (Zen) | Todo | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  | US1-9 | As a co-working space owner I want to delete my co-working space from the platform So that it is no longer visible or available for booking on the system | Design co-working space deletion confirmation UI flow | Papangkon (Nin) | Pongpanot (Munich) | Done | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Implement cascading deletion for space, rooms, and reservations API | Tanakit (Prom) | Khanaphat (Putter) | Done | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0
[5 empty] | Implement co-working space deletion frontend | Pongpanot (Munich) | Patarakrit (Zen) | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
[5 empty] | QA-Testing | Patarakrit (Zen) | Khanaphat (Putter) | Todo | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  |  |  | Task ทั้งหมด | 38
|  |  |  | หาร 9 | 8.4444
|  |  |  | Total Hours | 59 |  |  |  |  | 2026-04-11: จำนวน; 2026-04-13: Testing
|  |  |  | หาร 9 | 13.1111 |  |  | Todo | ยังไม่ select มาทำ | 2026-04-11: 9; 2026-04-13: Schemas
[8 empty] | Doing | กำลัง develop (design and code) | 2026-04-11: 0; 2026-04-13: UI Design
[8 empty] | Test | กำลัง test | 2026-04-11: 0; 2026-04-13: Frontend
[8 empty] | Done | ทำเสร็จ | 2026-04-11: 29; 2026-04-13: Backend
[8 empty] | Total | 59 | 59 | 52 | 43 | 40 | 40 | 39 | 39 | 39 | 39 | 27 | 0
Sprint Goal
Complete Co Working Space Managements related features
[5 empty] | Members | Hours
[5 empty] | Sutarasil (Jong) | 13
[5 empty] | Nathakorn (Oat) | 13
[5 empty] | Pongpanot (Munich) | 13
[5 empty] | Theerith (Jianfong) | 13
[5 empty] | Tanakit (Prom) | 14
[5 empty] | Khanaphat (Putter) | 13
[5 empty] | Papangkon (Nin) | 13
[5 empty] | Siravit (Bill) | 13
[5 empty] | Patarakrit (Zen) | 13
[5 empty] | Total/2 | 59